## Data Replication Runbook
Item | Dependency | Task details (Pre-Deployment tasks) | Owner | Category | Start date | Start time | End date | End time | Status | Activity logs
1 |  | Raise change request for CAB approval | Vignesh | Action | 2024-05-30 |  | 2024-05-30 |  | Completed
2 |  | ST,UAT & Integration testing signoff | Panos,Aziz,Senthil | Action | 2024-06-05 |  | 2024-06-05
3 | 1,2 | Presenting change request in CAB | Aziz | Action | 2024-06-05 |  | 2024-06-05
4 | 3 | Create SQL server user, role and access | Tesh | Action | 2024-06-05 |  | 2024-06-06
5 | 3 | Validate network connectivity set up done between AWS and SQL Server | Tesh | Validation | 2024-06-05 |  | 2024-06-06
6 | 3 | Check prod AWS environment availability including VPC and subnets | Aziz | Validation | 2024-06-05 |  | 2024-06-06
7 | 3 | Check access for AWS RX and RO group of users inclusing other service roles | Aziz | Validation | 2024-06-05 |  | 2024-06-06
8 | 3 | Create and share Dynamo DB details to store terraform state file in production | Kiran | Action | 2024-06-06 |  | 2024-06-07
9 | 3 | Create RDS instance and corresponding security groups | Kiran | Action | 2024-06-06 |  | 2024-06-07
10 | 3 | Create RDS PostgreSQl secret | Kiran | Action | 2024-06-06 |  | 2024-06-07
11 | 3 | Create SQL server secret | Kiran | Action | 2024-06-06 |  | 2024-06-07
12 | 3,8 | Create deploment pipeline | Aziz | Action | 2024-06-06 |  | 2024-06-10
13 | 3,8,9,10,11 | Update tfvar file for production | Aziz | Action | 2024-06-06 |  | 2024-06-10
Deployment tasks
14 | 13 | Validate DynamoDB,RDS & secrets are created and tfvar file is updated with all prod parameters | Aziz | Validation | 2024-06-11 |  | 2024-06-11
15 | 14 | Trigger deployment pipeline | Aziz | Action | 2024-06-12 |  | 2024-06-12
16 | 15 | Validate the AWS services created | Aziz/Sreekanth | Validation | 2024-06-12 |  | 2024-06-12 |  |  | Refer Post Deployment Validations
17 | 16 | Trigger post deployment script | Aziz | Action | 2024-06-12 |  | 2024-06-12
18 | 17 | Validate all databases and tables created acrossall 3 layers. | Aziz/Sreekanth | Validation | 2024-06-12 |  | 2024-06-12 |  |  | Refer Post Deployment Validations
19 | 18 | Trigger data ingestion job.(one off batch run) | Aziz | Action | 2024-06-12 |  | 2024-06-12
20 | 19 | Validate AWS and SQL Server connectivity. | Sreekanth | Validation | 2024-06-12 |  | 2024-06-12
| 20 | Validate data ingestion across all 3 layers | Sreekanth/Sandip | Validation | 2024-06-12 |  | 2024-06-12 |  |  | Validate data in Athena
Post Deployment tasks
21 | 20 | Select corresponding workgroup in Athena | BAU team | Action | 2024-06-13 |  | 2024-06-13
22 | 20 | Subscribe to SNS subscription for alerts. | BAU team | Action | 2024-06-13 |  | 2024-06-13
23 | 20 | Validate auto trigger of ingestion job on next day | Sreekanth/BAU team | Validation | 2024-06-13 |  | 2024-06-13 |  |  | Validate job run from console

## Post Deployment Validations
Validate the AWS services created
Component | AWS Component | Validation steps | Sub folders |  | Status | Comments
1 | S3 buckets | Validate below S3 buckets are deployed 1)tal-datareplication-metadata-bucket-ci 2)tal-datareplication-script-bucket-ci 3)tal-datareplication-athena-results-bucket-ci 4)tal-datareplication-rawdata-bucket-ci 5)tal-datareplication-processeddata-bucket-ci | tal-datareplication-script-bucket-ci Paths: adhoc/ under adhoc : athena_adhoc/ control_adhoc/ rds_adhoc/ athena_federated_lambda_function/ under lambda lambda_function.zip config/ under config config.txt Ext-Jars/ delta-core_2.12-1.0.0.jar mssql-jdbc-12.4.2.jre11.jar glue_job_scripts/ tal_datarep_adhoc_run_controller.py tal_datarep_dataingestion_controller_master.py tal_datarep_deployment_controller.py tal_datarep_deployment_pkg.zip tal_datarep_lib_pkg.zip master_controller/ failed/ input/ process/ success/ metadata/ control/ postdeployment/
2 | Glue jobs | Validate below Glue jobs are deployed 1) tal-datareplication-post-deployment-job-ci 2) tal-datareplication-data-ingestion-job-ci 3)tal-datareplication-adhoc-job-ci
3 | Glue connections | Validate Glue connections are depolyed tal-datareplication-mdm2a-connection-ci tal-datareplication-mdm2b-connection-ci tal-datareplication-talisman2a-connection-ci tal-datareplication-talisman2b-connection-ci tal-datareplication-rds2a-connection-ci tal-datareplication-rds2b-connection-ci
4 | Secret manager | rds_aurora_postgresql_credentials_ci tal-datareplication-OnPremSqlID-credentials-ci
5 | End points | tal-datareplication-sns-endpoint-ci tal-datareplication-glue-endpoint-ci
6 | Iam roles & policies
7 | VPC
8 | Subnet
9 | Security groups
10 | SNS | tal-datareplication-email-notification-topic-ci
11 | Lambda | tal-datareplication-athena-rds-postgresql-ci
12 | Data Sources (Federated Query) - Athena | tal-datareplication-postgresql-db-catalog-ci
13 | Work groups | tal-datareplication-athena-workgroup-ci
Validate all databases and tables created acrossall 3 layers.
1 | Athena | Validate Glue catalog Obejcts in Athena 1)Metadata Database: datareplication_metadata_ci 2)Control Tables: audit_logging batch batch_history bookmark column_mapping config ingestion_partition_config job job_batch source_system | Validate Glue catalog Obejcts in Athena 3)Raw Database(MDM): datareplication_mdm_raw_ci Tables: country_v_isocountry prisynccommon_v_commonexpiringisocountries prisynccommon_v_expenses prisynccommon_v_modelloading prisynccommon_v_planratios prisyncwk_v_globalinsight talbotlosscode_v_businessplanclass 4)Raw Database (Talisman): datareplication_talisman_raw_ci Tables: interfacedatalake_v_dimoriginalcurrency interfacedatalake_v_dimrisklocation interfacedatalake_v_fxrate_history interfacedatalake_v_policyextract | Validate Glue catalog Obejcts in Athena 5)Processed Database(MDM): datareplication_mdm_processed_ci Tables: business_plan_class common_expiring_iso_countries expenses global_insight iso_country model_loading plan_ratios 6)Processed Database(Talisman): datareplication_talisman_processed_ci Tables: dim_original_currency dim_risk_location fx_rate_history policy_extract
2 | RDS instance | Database: tal-datareplication-postgresql-db-catalog-ci Schema: pricing Tables: commonexpiringisocountries expense modelloading planratio politicalriskglobalinsight | Database: tal-datareplication-postgresql-db-catalog-ci Schema: reference Tables: businessplanclass currency fxrate geography isocountry | Database: tal-datareplication-postgresql-db-catalog-ci Schema: talismanextract Tables: policyfinancial

## Validation_after_first_run
Validation after first run
SNO | Validation Step | Owner | Status | Comments
1 | Check initial data load | Sreekanth
2 | Check metadata table updation | Sreekanth
3 | Validate full load in raw layer | Sreekanth
4 | Validate full load for incremantal tables | Sreekanth
5 | Validate type1 in processed layer | Sreekanth
6 | Validate type 2 in processed layer | Sreekanth
7 | Validate type 3 in processed layer | Sreekanth
8 | Validate data load in RDS PostgreSQl in corresponding schemas and tables | Sreekanth
9 | Validate batch and batch history tables | Sreekanth
10 | Validate job and job batch tables | Sreekanth
11 | Validate counts in audit logging table | Sreekanth
12 | Validate batchid in bookmark table | Sreekanth
Validation after second day
SNO | Validation Step | Owner | Status | Comments
1 | Check initial data load | Sreekanth
2 | Check metadata table updation | Sreekanth
3 | Validate full load in raw layer | Sreekanth
4 | Validate incremental load into raw layer based on bookmark table | Sreekanth
5 | Validate type1 in processed layer | Sreekanth
6 | Validate type 2 in processed layer | Sreekanth
7 | Validate type 3 in processed layer | Sreekanth
8 | Validate data load in RDS PostgreSQl in corresponding schemas and tables | Sreekanth
9 | Validate batch and batch history tables | Sreekanth
10 | Validate job and job batch tables | Sreekanth
11 | Validate counts in audit logging table | Sreekanth
12 | Validate batchid in bookmark table | Sreekanth

## Release candidates
Items | List all the release candidate to be added into the change
1 | S3 buckets
2 | Glue jobs
3 | Glue connections
4 | Athena
5 | RDS instance
6 | Secret manager
7 | End points
8 | Iam roles & policies
9 | VPC
10 | Subnet
11 | Security groups
12 | SNS
13 | Lambda
14 | Data Sources (Federated Query) - Athena
15 | Work groups

## Rollback plan
S.No | Action | Owner | Status | Comments
1 | Drop all control tables and database created using adhoc job | Sreekanth/Aziz
2 | Drop all Athena tables created using adhoc job | Sreekanth/Aziz
3 | Drop all postgreSQL tables and schemas created using adhoc job | Sreekanth/Aziz
4 | Destroy the environment using Azure devops pipeline | Aziz